## ECP Integration & Demonstration
[6 empty] | FY18 | [5 empty] | FY19 | [11 empty] | FY20
[6 empty] | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Task | Description | People | Person-Months |  | Dependencies | Apr. | May | Jun. | Jul. | Aug. | Sep. | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
1.1.0 | Development and verification of actuator line simulation capabilities | Maniaci |  |  | Work to develop actuator line and ABL models and Nalu so it is ready for use by WD, MMC, etc.…
1.1.1 | Neutral ABL with basic statistics, Wake slices | Blaylock | bar: Q3 Apr. to Q3 May
1.1.2 | Synthetic Lidar | Herges/Knaus | bar: Q3 May to Q3 Jun.
1.1.3 | Improved DAKOTA coupling for ABL and AL simulations | Frankel, Geraci | 1 PM, quarter time | 1 | meshing/nesting, precursor, UQ | bar: Q4 Aug. to Q1 Dec
1.1.4 | DAKOTA coupling for AAL | Frankel, Geraci | 0.5pm (.15 for 3 months) | 0 | AAL, moved to UQ | bar: Q3 Apr to Q3 Jun
1.1.5 | Mesh capability for active wake steering during simulation | Lawson, Shreyas | 3PM (.25 for 4qtr) | 3 | Overset group. Other method for wake movement? | bar: Q1 Oct to Q3 Jun
1.1.6 | Mixed Actuator Disc/AL | Tony, Matt C | 1PM | 1 | Actuator disc capability (Actuator Disk/Line Group) | bar: Q1 Oct to Q1 Dec
1.1.7 | DAKOTA link for MLMF sampling | Frankel | 1PM (.3 for 3 months) | 0 | moved to UQ, overlap WD | bar: Q3 Apr to Q3 Jun
1.1.8 | Wind farm inflow and wake stats advanced capibilities | Shreyas, Blaylock | 3PM (.25 for 4qtr) | 3 | Depends on gaps from WD validation studies | bar: Q1 Oct to Q4 Sep
1.1.9 | Initial Wake demonstration, single turbine, periodic, OpenFAST-AeroDyn | AF, MB, GG | 1 | 1 | UQ 3.1.2 | bar: Q1 Oct to Q4 Sep
1.1.10 | Wake demonstration for SWiFT dataset, neutral | AF, MB, GG | 2PM (.4 for 5 mo.) | 2 | UQ 3.1.3 | bar: Q1 Oct to Q4 Sep
1.1.11 | Publication on SWiFT neutral wake and loads study | AF, MB, GG, ME, DM | 1PM | 1 | UQ 3.1.4 | bar: Q1 Oct to Q4 Sep
1.1.12 | Validation with detailed wake experimental data, stable | AF, MB, GG | 3PM(.5 for 6 mo.) | 3 | UQ 3.1.6 | bar: Q1 Oct to Q4 Sep
1.1.13 | Validation with detailed wake experimental data, unstable | AF, MB, GG | 3PM(.5 for 6 mo.) | 3 | UQ 3.1.7 | bar: Q1 Oct to Q4 Sep
|  |  | Months | 18
2.1.0 | Wind farm simulation demonstration | Blaylock
2.1.1 | Stable boundary layer precursor [Critical, work will be performed in ABL area] | Blaylock / Shashank / Tony | 1PM @ quarter time | 0 | ABL eqn/IC/BC development | bar: Q1 Oct to Q1 Dec
2.1.2 | Unstable boundary layer precursor [Critical, work will be performed in ABL area] | Blaylock / Shashank / Tony | 1PM @ quarter time | 0 | ABL eqn/IC/BC development | bar: Q1 Oct to Q1 Dec
2.1.3 | 2-3 Turbine simulation with all 3 ABL types (Siemens 2.3 or SWiFT blades) | Ganesh / Blaylock | 2PM @ half time | 2 | Release of Siemens 2.3 geometry | bar: Q2 Jan to Q3 Jun
2.1.4 | Full wind farm simulations with all 3 ABL | Whole team | 2PM @ half time | 6 | bar: Q4 Jul to Q1 Dec
2.1.5 | Analyze and validate wind farm simulations | Whole team | TBD | 0 | Wake Dynamics | bar: Q1 Dec to Q3 Apr
|  |  | Months | 8
|  | Total Task 1+2 months | 26
|  | Total Task 1+2 FTE | 0.96296
3.1.0 | Blade resolved simulations | ML | Person Weeks
3.1.1 | Make determination on sliding or overset simulation capability | ML, SA | 2 | 0.5 | Overset team | bar: Q2 Jan to Q2 Mar
3.1.2 | Pursue NDA with Siemens for validation collaboration (i.e. ability to use Siemens 2.3 data/geometry) | ML | 2 | bar: Q2 Jan to Q2 Mar
3.1.3 | Decision on what turbine we will use for blade resolved simulations | ML, MS, SA |  | 0 | bar: Q2 Jan to Q2 Mar
3.1.4 | Develop single turbine mesh and test runs | ML | 4 | 1 | FSI capibility, RANS-LES capibiulity | bar: Q3 Apr to Q4 Sep
3.1.5 | Identify QOIs for single turbine simulation and wake | ML, SA, Mbar, MB, DM | 2 | 0.5 | bar: Q4 Jul to Q4 Aug
3.1.6 | Develop visualization and data processing strategy for single turbine | KG | 2 | 0.5 | bar: Q4 Jul to Q4 Aug
3.1.7 | Single turbine production run | ML, SA | 6 | 1.5 | bar: Q4 Jul to Q4 Sep
3.1.8 | Single turbine data processing and analysis | ML, SA, Mbar, DM | 6 | 1.5 | bar: Q1 Oct to Q2 Feb
3.1.9 | Develop two turbine mesh | ML | 10 | 2.5 | bar: Q2 Mar to Q3 May
3.1.10 | Identify QOIs for single turbine simulation and wake impingement | ML, SA, Mbar, MB, DM | 2 | 0.5 | bar: Q3 Apr to Q3 Jun
3.1.11 | Develop visualization and data processing strategy for single turbine | KG | 2 | 0.5 | bar: Q3 Apr to Q3 Jun
3.1.12 | Two turbine production runs | ML, SA | 8 | 2 | bar: Q3 Jun to Q4 Aug
3.1.13 | Two turbine data processing and analysis | ML, SA, Mbar, DM | 6 | 1.5 | bar: Q4 Aug to Q4 Sep
3.1.14 | NREL 5 MW data processing and publication | ML | 8 | 2 | bar: Q1 Oct to Q1 Dec
|  |  | Months | 14.5
40.5
| Yellow cell indicate decision points and/or milestones |  | FTE | 1.5
Uncertinity and coordination between the ABL team and the integration/demo team is needed
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1

## Notes
Notes: Is there a disconnect between WD and HFM/ECP? How can this be improved? A high level question for A2e management / Pis

## ValidationCases
Validation cases
Initial SWiFT case | Q3 Fy18
SWiFT UQ Case | Q4 FY18
SWiFT stable case | Q2Fy18
SWiFT Unstable case | Q3FY18
SWiFT stable, active Wake steering | Q4Fy18
SWiFT MLMF statistical analysis | Q2FY19
DanAero blade?
Siemens blade?
GE?
Rodsand II
OWEZ
MEXICO
Phase VI
…